## Summary Sheet FS
Directoroate of Environment & Climate Change
Action Plan for Clean Air-Nine Non attainment cities
Summary : Activities related to Department of Food & Civil Supplies
Sr No. | Activity | Measuring units/ Performance Indicator | Baseline as on 31.03.2019 | Targets | Timeline | Progress as on 30.04.2019 | Progress as on 31.05.2019 | Remarks of DECC
1 | CIE 2(ii) Progress regarding creation of infrastructure for CNG Pipeline (Deptt. of Food & Civil Supplies) | Pipleline to be laid (Km) | 67.12 | 51.55 | 31.03.2021 | DFSC informed that information relates to Local Government as per Notification dated 16.04.2018
2 | CVE 5 - Progress regarding checking of Fuel Adulteration (Deptt. Food & Civil Supplies) | i) No. of inspections carried out, ii) No. of violations observed | i) 0 Ii) 0 | Regular inspections of the Petrol Pumps | Regular Activity | 0
3 | CVE 11 (a) – Progress regarding infrastructure development for CNG based public transport (Deptt. of Food & Civil Supplies) | No. of existing CNG Stations | 9 | 20 | 31.03.2020 | 01 nos conventional Station upgraded to CNG

## CIE 2(ii) FS
Proforma- H-1
CIE 2(ii) Progress regarding creation of infrastructure for CNG Pipeline (Deptt. of Food & Civil Supplies)
Sr. No. | Name of city | Baseline as on 31.03.2019 (Pipeline already laid) (Km) | Targets (Pipleline to be laid) (Km) | Timeline | Progress of May,2019 | Cumm. progress as on 31.05.19 | Remarks of concerned Deptt./officer (If any) | Remarks of DECC
[5 empty] | Pipeline laid (Km) | Pipeline laid (Km)
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9
1 | Mandi Gobindgarh | 38.8 | 19.85 | 31.03.2021 | - | -
2 | Khanna | 0 | 0 | NA | - | -
3 | Jalandhar | 0 | 0 | NA | - | -
4 | Ludhiana | 12.12 | 21.7 | 31.03.2021 | - | -
5 | Patiala | 0 | 0 | NA | - | -
6 | Amritsar | 16.2 | 10 | 31.03.2021 | - | -
7 | Nayan Nangal | 0 | 0 | NA | - | -
8 | DeraBassi | 0 | 0 | NA | - | -
9 | Dera Baba Nanak | 0 | 0 | NA | - | -
| Total | 67.12 | 51.55

## CVE 5 FC
Proforma- H-2
CVE 5 - Progress regarding checking of Fuel Adulteration (Deptt. of Food & Civil Supplies)
Sr. No. | Name of city | Baseline as on 31.03.2019 |  | Targets | Timeline | Progress of May,2019 |  | Cumm. progress as on 31.05.2019 |  | Remarks of concerned Deptt./ officer (If any) | Remarks of DECC
|  | No. of inspections carried out | No. of violations observed |  |  | No. of inspections carried out | No. of violations observed | No. of inspections carried out | No. of violations observed
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 7 | 8 | 9 | 10
1 | Mandi Gobindgarh | 0 | 0 | Regular inspections of the Petrol Pumps and if any descrepancy is noticed then action against the violators shall be taken | Regular
2 | Khanna | 0 | 0
3 | Jalandhar | 0 | 0
4 | Ludhiana | 0 | 0
5 | Patiala | 0 | 0
6 | Amritsar | 0 | 0
7 | Nayan Nangal | 0 | 0
8 | DeraBassi | 0 | 0
9 | Dera Baba Nanak | 0 | 0
| Total | 0 | 0

## CVE 11 (a) FC
Proforma- H-3
CVE 11 (a) – Progress regarding infrastructure development for CNG based public transport (Deptt. of Food & Civil Supplies)
Sr. No. | Name of city | Baseline as on 31.03.2019 | Targets |  | Timeline | Progress as on 30.04.2019 |  | Progress of May,2019 |  | Cumm. progress as on 31.05.2019 |  | Remarks of concerned Deptt./ officer (If any) | Remarks of DECC
|  | No. of existing CNG Stations | No. of new CNG Station to be set up | No. of conventional staions to be upgraded to CNG |  | No. of new CNG Station set up | No. of conventional staions upgraded to CNG | No. of new CNG Station set up | No. of conventional staions upgraded to CNG | No. of new CNG Station set up | No. of conventional staions upgraded to CNG
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 7 | 8 | 7 | 8 | 11 | 12
1 | Mandi Gobindgarh | 1 | 0 | 2 | 31.03.2020 | 0 | 1
2 | Khanna | 0 | 0 | 0 | NA | 0 | 0
3 | Jalandhar | 2 | 0 | 1 | 31.03.2020 | 0 | 0
4 | Ludhiana | 3 | 1 | 1 | 31.03.2020 | 0 | 0
5 | Patiala | 0 | 0 | 2 | 31.03.2020 | 0 | 0
6 | Amritsar | 3 | 1 | 10 | 31.03.2020 | 0 | 0
7 | Nayan Nangal | 0 | 0 | 0 | NA | 0 | 0
8 | DeraBassi | 0 | 0 | 2 | 31.03.2020 | 0 | 0
9 | Dera Baba Nanak | 0 | 0 | 0 | NA | 0 | 0
| Total | 9 | 2 | 18 |  | 0 | 1
Note on D3: hp: Baseline data not added in the target