## Summary Sheet PSIEC
Directoroate of Environment & Climate Change
Action Plan for Clean Air-Nine Non attainment cities
Summary of Activities related to PSIEC
Sr No. | Activity | Measuring units/ Performance Indicator | Baseline as on 31.03.2019 | Targets | Timeline | Progress as on 31.05.2019
1 | CIE 5:Shifting of industries from non-designated area to industrial Area (Deptt. of Industries & Commerce,Department of Town & Country Planning and Local Government) | Identified industries to be shifted to designated area | 196 | 196 | 31.08.2025
2 | CRD 4(ii) - Progress regarding creation of green buffers along road side (PSIEC) | No. of trees/shrubs planted | 1850 | 1325 | Regular Activity
3 | CRD 7 (b) - Progress regarding Existing roads requiring recarpeting (MC,PWD,PUDA,PSIEC) | Existing roads requiring recarpetting) (Km) | 347.45 | 347.45 | 31.03.2021

## CRD 4(ii) PSIEC
Proforma G-1
CRD 4(i) - Progress regarding creation of green buffers along road side (PSIEC)
Sr. No. | Name of city | Baseline as on 31.03.2019 |  | Targets |  | Timeline | Progress of May,2019 |  | Cumm. progress as on 31.05.2019 |  | Remarks of concerned Deptt./ officer (If any) | Remarks of DECC
|  | Total road length identified for creating green buffer (Km) | No of trees planted | Identified road sides to be brought under green buffer (Km) | No. of trees/ shrubs to be planted |  | Road sides brought under green buffer (Km) | No. of trees/shrubs planted | Road sides brought under green buffer (Km) | No. of trees/shrubs planted
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 8 | 9 | 10 | 11
1 | Mandi Gobindgarh |  | 800 |  | 550 | Regular activity
2 | Khanna |  | 0 |  | 0
3 | Jalandhar |  | 0 |  | 0
4 | Ludhiana |  | 0 |  | 0
5 | Patiala |  | 0 |  | 0
6 | Amritsar |  | 0 |  | 0
7 | Nayan Nangal |  | 250 |  | 375
8 | DeraBassi |  | 800 |  | 400
9 | Dera Baba Nanak |  | 0 |  | 0
| Total | 0 | 1850 | 0 | 1325
Note on J3: hp: Progrss of April,19+ May,19+…....

## CRD 7(b-iv) PSIEC
Proforma G-2
CRD 7 (b) - Progress regarding Existing roads requiring recarpeting (PSIEC)
Sr. No. | Name of city | Baseline as on 31.03.2019 (Total length of exisiting roads) (Km) | Targets (Existing roads requiring recarpetting) (Km) | Timeline | Progress of May,2019 |  |  | Cumm. progress as on 31.05.2019 | Remarks of concerned Deptt./ officer (If any) | Remarks of DECC
[5 empty] | Tendering (Completed or Under Process) | Work allotment (Completed or Under Process) | Status of Work (Completed or in progress) (km) | Existing roads recarpeted (Km)
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 |  | 9 | 10
1 | Mandi Gobindgarh | 9 | 9 | 30.06.2019
2 | Khanna | 0 | 0 | NA
3 | Jalandhar | 7 | 7 | 31.03.2020
4 | Ludhiana | 0 | 0 | NA
5 | Patiala | 0 | 0 | NA
6 | s | 10 | 10 | 31.03.2020
7 | Nayan Nangal | 2.9 | 2.9 | 31.03.2020
8 | DeraBassi | 3 | 3 | 31.12.2019
9 | Dera Baba Nanak | 0 | 0 | NA
| Total | 31.9 | 31.9
City-wise details of existing roads to be recarpeted - Supplementary Information
Name of the city :
Sr.No. | Name of the existing roads to be recarpeted |  |  | Road length (Kms)

## CIE 5(i) Ind
Proforma G-3
CIE 5 (i):Shifting of industries from non-designated area to industrial Area (Deptt. of Industries & Commerce)
Sr. No. | Name of city | Baseline as on 31.03.2019 | Targets | Timeline | Progress as on 31.05.2019 | Remarks of concerned officer (If any) | Remarks of DECC
|  | Total number of industries identifed which are located in non designated areas | Identified industries to be shifted to designated area |  | No. of industries shifted to designated area
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8
1 | Mandi Gobindgarh | 10 | 10 | 23.06.2021
2 | Khanna | 30 | 30 | 03.01.2021
3 | Jalandhar | 11 | 11 | 31.08.2025
4 | Ludhiana | 103 | 103 | 31.08.2023
5 | Patiala | 12 | 12 | 31.12.2024
6 | Amritsar | 30 | 30 | -
7 | Nayan Nangal | - | - | -
8 | DeraBassi | - | - | -
9 | Dera Baba Nanak | 0 | 0 | NA
| Total | 196 | 196

## CRD 1 (iv) PSIEC
CRD 1 (iv) : Maintain pothole free roads /Patch work of roads (PSIEC)
Sr. No. | Name of city | Baseline as on 31.03.2019 (Total road length with potholes Identified) (Km) | Targets (Identified road length to be made pothole free) (Km) | Timeline | Progress of May,2019 |  |  | Cumm. progress as on 31.05.2019 | Remarks of concerned Deptt./officer (If any) | Remarks of DECC
[5 empty] | Tendering (Completed or Under Process) | Work allotment (Completed or Under Process) | Status of Work (Completed or in progress) (km) | Identified road length made pothole free) (Km
1 | 2 | 3 | 4 | 5 | 6 | 7 |  |  | 8 | 9
1 | Mandi Gobindgarh | 0 | 0 | NA
2 | Khanna | 0 | 0 | NA
3 | Jalandhar | 0 | 0 | NA
4 | Ludhiana | 0 | 0 | NA
5 | Patiala | 0 | 0 | NA
6 | Amritsar | 0 | 0 | NA
7 | Nayan Nangal | 0 | 0 | NA
8 | DeraBassi | 0 | 0 | NA
9 | Dera Baba Nanak | 0 | 0 | NA
City-wise details of roads made pothole free - Supplementary Information
Name of the city :
Sr.No. | Name of the road to be made pothole free |  |  | Road length (Kms)