## CR5-Local Govt-Existing STP.
Sr. No. | River | Name of Town | District | Deptt. | Cap. (MLD) | Actual Discharge received (MLD) | Quantity of Wastewater treated (MLD) | Tech. | Design Parameters |  |  | Baseline (March, 19) Results by PPCB |  |  | PPCB Results for the current Month |  |  | Sr. No | Name of Town | Reasons for Non-Compliance | [5 empty] | Payment made to Operator upto Month | Penalty deducted from Operator Payment for Non Compliance | Responsible Officer | Timeline to achieve prescribed standards in case of non-compliance
[9 empty] | BOD (mg/l) | TSS (mg/l) | FC (MPN/ 100ml) | BOD (mg/l) | TSS (mg/l) | FC (MPN/ 100ml) | BOD (mg/l) | TSS (mg/l) | FC (MPN/ 100ml) |  |  | Lack of O&M funds | Component Breakdown | Non-availability of Power | Non-availability of Chlorine | Lack of Skilled Manpower | Any other reason
1 | 2 | 3 | 4 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31

## CR6-Existing STP-Sludge
Sr. No. | Sr. No | Location of STP | Capacity (MLD) | Present Capacity at which STP is operated (MLD) | Tech. | Quantity of Sludge Greneration as per design of STP from Aeration Tank (m3/day) | Quantity of Sludge recirculated/wasted (m3/day) |  | Actual Quanity of Sludge Genreated after de-watering for disposal during the Month (Kg) | Quantity of Sludge disposed off out of t he quantity generated during the month and where the same has been disposed off (Kg) | Balanace Quantity of sludge lying in the premises of STP of previous Month (Kg) | Balance quantity of Sludge lying at the STP at end of Month (Kg)
[7 empty] | Recirculated | Wasted
1 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12=(9+11)-10

## CR14- New STPs
Sr. No. | River | District | Name of STP | Concerned Deptt. | Cap. (MLD) | Tech. | Status of Funds |  | Baseline Target Dates as per Action Plan (March 19) |  |  |  | Current Status i.e Date of completion or likely date of completion |  |  |  | Reason in case of delay | Responsible Officer
[7 empty] | Tied Up | Not Tied Up | Preparation of DPR | Tendering | Commencement of work | Completion & Commissioning | Preparation of DPR | Tendering | Commencement of work | Completion & Commissioning
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19

## CR16-MCL- New ETP-Biogas Plant
S. No. | Description of ETP | Cap. (MLD) | Status of Funds |  | Baseline (March 19) |  |  |  | Current Progress i.e Date of Completion or likely date of completion |  |  |  | Reasos for delay
|  |  | Tied Up | Not Tied Up | Preparation of DPR | Tendering | Commencement of work | Completion & Commissioning | Preparation of DPR | Tendering | Commencement of work | Completion & Commissioning
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14

## CR17- MCJ-Dairy ETP
S. No. | Description of ETP | Cap. (MLD) | Status of Funds |  | Baseline (March 19) |  |  |  | Current Progress i.e Date of Completion or likely date of completion |  |  |  | Reasos for delay
|  |  | Tied Up | Not Tied Up | Preparation of DPR | Tendering | Commencement of work | Completion & Commissioning | Preparation of DPR | Tendering | Commencement of work | Completion & Commissioning
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14

## CR20- OCMS-STPs- MCs-ULBs
Sr. No. | River | Location of STP | District | Concerned RO | Capacity (MLD) | Baseline (March 19) |  |  |  | Current Progress i.e Date of Completion or likely date of completion
[6 empty] | Procurment Process | Finalization of Supply orders | Installation of online continuous monitoring system | Commissioning | Procurment Process | Finalization of Supply orders | Installation of online continuous monitoring system | Commissioning
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14