## Summary Sheet DOT
Directoroate of Environment & Climate Change
Action Plan for Clean Air-Nine Non attainment cities
Summary : Activities pertaining to Deptt.of Transport
Sr No. | Activity | Measuring units/ Performance Indicator | Baseline as on 31.03.2019 | Targets | Timeline | Progress as on 31.05.2019
1 | CVE 1 - Progress regarding Public awareness campaign for control of vehicular emissions (DOT) | Nos of Public awareness campaigns | 29 | 234 | Regular Activity
2 | CVE 2 - Progress regarding setting up of Remote Sensor Based PUC System (DOT & PPCB) | Nos of PCCs in the City to be linked with VAHAN 4.0 software | 0 | All PCC of city to be linked wih Vahan 4.0 Software | 30.06.2020
3 | CVE 9 - Progress regarding phasing out commercial diesel vehicles more than 15 years old (Deptt. of Transport) | Policy matter | New commercial diesel vehicles is registered for 2 years and thereafter, fitness certificate is being issued every year | Matter of fixing the age of commercial diesel vehicles to be examined legally | 31.03.2020
4 | CVE 10 - Progress regarding promotion of E-Vehicles (DOT) | Policy matter | Policy is in the final stages | After approval from Competent Authority E- Vehicle policy will be notified. | 31.03.2020
5 | CVE 11 (c) – Progress regarding introduction of CNG based autos/taxis (DOT) | No. of CNG based autos/taxis | 0 | 0 | 31.03.2022

## CVE 1 i DOT
Proforma E-1
CVE 1 - Progress regarding Public awareness campaign for control of vehicular emissions (Deptt. of Transprot)
Sr. No. | Name of city | Baseline as on 31.03.2019 | Targets (No. of awareness activites to be organized during 2019) | Timeline | Progress of May,2019 |  | Cumm. progress as on 31.05.2019 |  | Remarks of concerned Deptt./ officer (If any) | Remarks of DECC
|  | No. of awareness activities organized |  |  | No. of awareness activities organised | No of Participants | No. of awareness activities organised | No of Participants
1 | 2 | 3 | 4 | 5 | 6 | 7 | 6 | 7 | 8 | 9
1 | Mandi Gobindgarh | 0 | 26 | 30.09.2019 |  | 17 |  | 17
2 | Khanna | 0 | 26
3 | Jalandhar | 12 | 26
4 | Ludhiana | 0 | 26
5 | Patiala | 5 | 26
6 | Amritsar | 0 | 26
7 | Nayan Nangal | 11 | 26
8 | DeraBassi | 1 | 26
9 | Dera Baba Nanak | 0 | 26
| Total | 29 | 234 | 30.09.2019
Note on H3: hp: Cumm. Progress includes the progress of April19 + May,19+…..

## CVE 2 (DOT)
Proforma E-2
CVE 2 - Progress regarding setting up of Remote Sensor Based PUC System (Deptt. of Transport & PPCB)
Sr. No. | Name of city | Baseline as on 31.03.2019 | Targets (No. of PCC to be linked with VAHAN 4.0 software of the Transport Deptt. | Timeline | Cumm. progress as on 31.05.2019 |  | Remarks of concerned Deptt./ officer (If any) | Remarks of DECC
|  | No. of PCCs in the City to be linked with VAHAN 4.0 software of the Transport Deptt.) |  |  | Status of development of software for linking of PCCs (Developed/ Under development) | No. of PCCs linked
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9
1 | Mandi Gobindgarh |  |  | 30.06.2020
2 | Khanna
3 | Jalandhar
4 | Ludhiana
5 | Patiala
6 | Amritsar
7 | Nayan Nangal
8 | DeraBassi
9 | Dera Baba Nanak
| Total |  | 550

## CVE 9 DOT
Proforma E-3
CVE 9 - Progress regarding phasing out commercial diesel vehicles more than 15 years old (Deptt. of Transport)
Sr. No. | Name of city | Baseline as on 31.03.2019 | Targets | Timeline | Cumm. progress as on 31.05.2019 | Remarks of concerned Deptt./ officer (If any) | Remarks of DECC
Status of the legal review of the matter
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8
1 | Mandi Gobindgarh | New commercial diesel vehicles is registered for 2 years and thereafter, fitness certificate is being issued every year | Matter of fixing the age of commercial diesel vehicles to be examined legally | One year
2 | Khanna
3 | Jalandhar
4 | Ludhiana
5 | Patiala
6 | Amritsar
7 | Nayan Nangal
8 | DeraBassi
9 | Dera Baba Nanak

## CVE 10 DOT
Proforma E-4
CVE 10 - Progress regarding promotion of E-Vehicles (Deptt. of Transport)
Sr. No. | Name of city | Baseline as on 31.03.2019 |  | Targets | Timeline | Cumm. progress as on 31.05.2019 |  | Remarks of concerned Deptt./ officer (If any) | Remarks of DECC
|  | Framing of E-vehicle policy | No. of E-vehicles plying on the road |  |  | Status of framing of E-vehicle policy | No. of E-vehicles plying on the road
1 | 2 | 3 |  | 4 | 5 | 6 |  | 7 | 8
1 | Mandi Gobindgarh | Policy is in the final stages. | 0 | After approval from Competent Authority E- Vehicle policy will be notified. | One year
2 | Khanna |  | 0
3 | Jalandhar |  | 0
4 | Ludhiana |  | 0
5 | Patiala |  | 0
6 | Amritsar |  | 2500
7 | Nayan Nangal |  | 0
8 | DeraBassi |  | 0
9 | Dera Baba Nanak |  | 0
Total

## CVE 11 (C) DOT
Proforma E-5
CVE 11 (c) – Progress regarding introduction of CNG based autos/taxis (Deptt.of Transport)
Sr. No. | Name of city | Baseline as on 31.03.2019 | Targets | Timeline | Cumm. progress as on 31.05.2019 | Remarks of concerned Deptt./ officer (If any) | Remarks of DECC
|  | No. of CNG based autos/taxis | Measures to be taken to introduce CNG autos/ taxis |  | Measures taken to introduce CNG autos/taxis
1 | 2 | 3 | 4 | 6 | 7 | 11 | 12
1 | Mandi Gobindgarh | PPCB has issued direction vide letter no 05 dated 03.01.2019 under section 31-A of Air Act 1981 to stop registration of new diesel / petrol driven auto rickshaw (s), in 5 districts including Fatahgarh saahib, khanna, Jalandhar, ludhiana,Amritsar w.e.f 01.02.2019. | Implementatin of PPCB orders dated 03.01.2019 | 31.03.2022
2 | Khanna
3 | Jalandhar
4 | Ludhiana
5 | Amritsar
6 | Patiala | 0
7 | Nayan Nangal | 0
8 | DeraBassi | 0
9 | Dera Baba Nanak | 0
| Total | 0