## Summary Sheet MC
Directoroate of Environment & Climate Change
Action Plan for Clean Air-Nine Non attainment cities
Summary : Activities pertaining to MC
Sr No. | Activity | Measuring units/ Performance Indicator | Baseline as on 31.03.2019 | Targets | Timeline | Progress as on 30.04.2019
1 | CRD 1 (i) : Maintain pothole free roads /Patch work of roads (MC) | Identified road length made pothole free (Km) | 201.45 | 201.45 | 30.11.2019
2 | CRD 2 (i) : Progress regarding water sprinkling (MC) | Total road length to be sprinkled (Km) | 157 | 157 | Regular Activity
3 | CRD 2 (ii) : Progress regarding procurement of water sprinklers (MC) | No. of sprinklers procured | 15 | 13 | 31.03.2020
4 | CRD 3 : Progress regarding Mechanical sweeping of roads (MC) | No. of mechanical sweepers procured | 0 | 13 | 31.03.2020
5 | CRD 4(i) - Progress regarding creation of green buffers along road side (MC) | No. of trees/shrubs planted | 2000 | 28325 | Regular Activity | 24
6 | CRD 5 - Progress regarding Greening of parks, open areas, community places, schools and housing societies (MC) | No. of trees/shrubs planted | - | 53850 | Regular Activity
7 | CRD 6 - Progress regarding Water fountains at major traffic intersections (MC) | No. of chowks/ intersections installed with water fountain) | 14 | 7 | 31.03.2020
8 | CRD 7 (a-i) - Progress regarding Kaccha/Brick Paved Roads to be made Pucca road (MC) | Katcha /Brick Paved roads made pucca road (Km) | 80.36 | 80.36 | 31.03.2021
9 | CRD 7 (b-i) - Progress regarding Existing roads requiring recarpeting (MC) | Existing roads requiring recarpetting) (Km) | 206.56 | 206.56 | 31.03.2021
10 | CRD 7 (c-i) -Pavement of road side using interlocking tiles(MC) | Length of berm stabilized by using interlocking tiles (Km) | 61.4 | 61.4 | 31.03.2020
11 | CVE 4 (a -i) - Progress regarding Prevent parking of vehicles in non-designated areas by enforcement actions (MC) | Nos of"No Parking” sign Boards installed | 277 | 294 | 31.12.2019
12 | CVE 4 (a-ii) - Progress regarding Prevent parking of vehicles in non-designated areas by enforcement actions (Traffic Police) | No. of challans | 37116 | Regular inspection and challaning of vehicles parked in the non-designated areas | Regular Activity
13 | CVE 6 (a) - Progress regarding Widening of roads and infrastructure for decongestion of roads (MC) | Total road length identified for widening (Km), | 48.1 | 48.1 | 31.03.2020
14 | CVE 6(b) - Progress regarding Road design improvement (MC) | Road length constructed after proper redesigning (Km) | 40 | 16.7 | 31.3.2021
15 | CVE 7 - Progress regarding intelligent traffic systems (MC) | No. of intellegent traffic lights already installed | 0 | 53 | 31.03.2020
16 | CVE 8 - Progress regarding Construction of expressways/ bypasses to avoid congestion (MC ) | Existing No. of bypass/ expressways | 0 | 1 | 30.06.2021
17 | CVE 11 (b) – Progress regarding introduction of CNG based city Bus Service (MC) | No. of CNG based buses | 0 | 0 | 31.03.2022
18 | CBGB 1 – Control on open burning of bio-mass in City (MC) | Nos of Composting Pits | 0 | 856 | 31.03.2020
19 | CBGB 2 – Control on burning of municipal solid wastes (MC) | Nos of Insection made | 0 | 0 | 30.09.2019
20 | CCDA 1 (a) – Enforcement of Construction & Demolition Waste Rules (MC) | Nos of Inspection made | 270 | 1260 | 30.09.2019
21 | CCDA 1 (b) –Development of Infrastructure of Construction & Demolition waste (MC) | No. of sites to be developed for C& D Waste disposal | 19 | 20 | 31.03.2022
22 | CCDA 2 – Progress regarding control measures for fugitive measures w.r.t Construction & Demolition Activities (MC) | Nos of Inspection made | 80 | 360 | 30.09.2019
23 | CCDA 3 – Control measures for carrying the construction material enclosed/ covered vessels (MC) | Nos of Inspection made | 0 | 360 | 30.09.2019

## CRD 1(i)MC
Proforma B-1
CRD 1 (i) : Maintain pothole free roads /Patch work of roads (MC)
Sr. No. | Name of city | Baseline as on 31.03.2019 (Total road length with potholes Identified) (Km) | Targets (Identified road length to be made pothole free) (Km) | Timeline | Progress of May 2019 |  |  | Cumm. progress as on 31.05.2019 | Remarks of concerned Deptt./officer (If any) | Remarks of DECC
[5 empty] | Tendering (Completed or Under Process) | Work allotment (Completed or Under Process) | Status of Work (Completed or in progress) | (Identified road length made pothole free) (Km)
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 |  | 9 | 10
1 | Mandi Gobindgarh | 5 | 5 | 30.10.2019
2 | Khanna | 3 | 3 | 30.11.2019
3 | Jalandhar | 14.9 | 14.9 | 31.03.2021
4 | Ludhiana | 167 | 167 | 30.11.2019
5 | Patiala | 1.375 | 1.375 | 30.10.2019
6 | Amritsar | 4 | 4 | 30.09.2019
7 | Nayan Nangal | 1.175 | 1.175 | 31.10.2019
8 | DeraBassi | 4 | 4 | 31.07.2020
9 | Dera Baba Nanak | 1 | 1 | 31.10.2019
| Total | 201.45 | 201.45
City-wise details of roads made pothole free - Supplementary Information
Name of the city :
Sr.No. | Name of the road to be made pothole free |  |  | Road length (Kms)

## CRD 2(i) MC
Proforma B-2
CRD 2 (i) : Progress regarding water sprinkling (MC)
Sr. No. | Name of city | Baseline as on 31.03.2019 (Total road length identified for sprinkling) (Km) | Targets (Total road length to be sprinkled (Km) | Timeline | Progress as on 30.04.2019 (roads sprinkled in kms) | Remarks of concerned Deptt./officer (If any) | Remarks of DECC
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8
1 | Mandi Gobindgarh | 5.6 | 5.6 | Regular activity
2 | Khanna | 10 | 10
3 | Jalandhar | 9 | 9
4 | Ludhiana | 41.5 | 41.5
5 | Patiala | 16.4 | 16.4
6 | Amritsar | 67.5 | 67.5
7 | Nayan Nangal | 1 | 1
8 | DeraBassi | 5 | 5
9 | Dera Baba Nanak | 1 | 1
| Total | 157 | 157
City-wise details of roads identified for water sprinkling - Supplementary Information
Name of the city :
Sr.No. | Name of the roads identified for water sprinkling |  |  | Road length (Kms)

## CRD 2(ii) MC
Proforma B-3
CRD 2 (ii) : Progress regarding procurement of water sprinklers (MC)
Sr. No. | Name of city | Baseline as on 31.03.2019 (No. of existing water sprinklers) | Targets (No. of sprinklers to be procured) | Timeline | Progress as on 30.04.2019 |  |  | Remarks of concerned Deptt./ officer (If any) | Remarks of DECC
[5 empty] | Tendering (Completed or Under Process) | Purchase of Machines (Purched/ Under Process) | No. of Sprinklers working
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10
1 | Mandi Gobindgarh | 1 | 2 | 30.10.2019
2 | Khanna | 1 | 2 | 31.03.2020
3 | Jalandhar | 2 | 0 | NA
4 | Ludhiana | 2 | 2 | 31.12.2019
5 | Patiala | 1 | 2 | 31.01.2020
6 | Amritsar | 3 | 2 | 31.12.2019
7 | Nayan Nangal | 2 | 0 | NA
8 | DeraBassi | 2 | 3 | 31.01.2020
9 | Dera Baba Nanak | 1 | 0 | NA
| Total | 15 | 13

## CRD 3 MC
Proforma B-4
CRD 3 : Progress regarding Mechanical sweeping of roads (MC)
Sr. No. | Name of city | Baseline as on 31.03.2019 |  | Targets |  | Timeline | Progress as on 30.04.2019 |  | Remarks of concerned Deptt./officer (If any) | Remarks of DECC
|  | No. of existing mechanical sweepers | Road length identified for mechanical sweeping (Kms) | No. of mechanical sweepers to be procured | Road length to be mechanically sweeped (Km) |  | Mechanical Sweeping Machines procured (Nos ) | Road length mechanically sweeped (Km)
1 | 2 | 4 | 3 | 6 | 5 | 7 | 8 | 10 | 11 | 12
1 | Mandi Gobindgarh | 0 | 7.5 | 1 | 7.5 | 31.03.2020
2 | Khanna | 0 |  | 2 |  | 31.03.2020
3 | Jalandhar | 0 |  | 2 |  | 31.03.2020
4 | Ludhiana | 0 | 90 | 4 | 90 | 31.03.2020
5 | Patiala | 0 | 0 | 0 | 0 | NA
6 | Amritsar | 0 | 55.07 | 2 | 55.07 | 31.03.2020
7 | Nayan Nangal | 0 | 10 | 2 | 10 | 31.03.2020
8 | DeraBassi | 0 |  | 0 |  | NA
9 | Dera Baba Nanak | 0 |  | 0 |  | NA
| Total | 0 | 162.57 | 13 | 162.57
City-wise details of roads identified for mechanical sweeping - Supplementary Information
Name of the city :
Sr.No. | Name of the road identified for mechanical sweeping |  |  | Road length (Kms)

## CRD 4(i) MC
Proforma B-5
CRD 4(i) - Progress regarding creation of green buffers along road side (MC)
Sr. No. | Name of city | Baseline as on 31.03.2019 |  | Targets |  | Timeline | Progress as on 30.04.2019 |  | Remarks of concerned Deptt./ officer (If any) | Remarks of DECC
|  | Total road length identified for creating green buffer (Km) | No of trees planted | Identified road sides to be brought under green buffer (Km) | No. of trees/ shrubs to be planted |  | Road sides brought under green buffer (Km) | No. of trees/shrubs planted
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11
1 | Mandi Gobindgarh | 12 | - | 12 | 3000 | Regular activity
2 | Khanna | 6 | - | 6 | 500
3 | Jalandhar | 60 | - | 60 | 4000
4 | Ludhiana | 7.8 | - | 7.8 | 12000
5 | Patiala | 2.2 | - | 2.2 | 4775
6 | Amritsar | 4 | 1000 | 4 | 2000
7 | Nayan Nangal | 9 | - | 9 | 600
8 | DeraBassi |  | 1000 |  | 1350
9 | Dera Baba Nanak | - | - | - | 100
| Total | 101 | 2000 | 101 | 28325

## CRD 5 MC
Proforma B-6
CRD 5 - Progress regarding Greening of parks, open areas, community places, schools and housing societies (MC)
Sr. No. | Name of city | Baseline as on 31.03.2019 (Total number of parks) | Targets |  | Timeline | Progress as on 30.04.2019 |  | Remarks of concerned Deptt./officer (If any) | Remarks of DECC
|  |  | Sites/ parks identified for greening (No.) | No. of trees/ shrubs to be planted |  | No. of parks brought under greening | No. of trees/shrubs planted
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10
1 | Mandi Gobindgarh | 11 | 5 | 3000 | Regular activity
2 | Khanna | 45 | 10 | 9500
3 | Jalandhar | 475 | 100 | 12700
4 | Ludhiana | 870 | - | 24200
5 | Patiala | 112 | - | 1100
6 | Amritsar | 395 | - | 3000
7 | Nayan Nangal | 42 | - | -
8 | DeraBassi | 8 | 8 | 350
9 | Dera Baba Nanak | 0 | 0 | 0
| Total | 1958 | 123 | 53850
Note on E9: Author: to be planted by DFO

## CRD 6 MC
Proforma B-7
CRD 6 - Progress regarding Water fountains at major traffic intersections (MC)
Sr. No. | Name of city | Baseline as on 31.03.2019 (Existing No. of water fountains) | Targets (No. of chowks/ intersections to be installed with water fountain) | Timeline | Progress as on 30.04.2019 (No. of chowks/ intersections installed with water fountain) | Remarks of concerned Deptt./officer (If any) | Remarks of DECC
1 | 2 | 3 | 4 | 5 | 6 | 8 | 9
1 | Mandi Gobindgarh | 0 | 1 | 30.11.2019
2 | Khanna | 0 | 0 | NA
3 | Jalandhar | 10 | 0 | NA
4 | Ludhiana | 3 | 0 | NA
5 | Patiala | 1 | 0 | NA
6 | Amritsar | 0 | 3 | 31.03.2020
7 | Nayan Nangal | 0 | 2 | 31.03.2020
8 | DeraBassi | 0 | 0 | NA
9 | Dera Baba Nanak | 0 | 1 | 31.03.2020
| Total | 14 | 7

## CRD 7 (a-i) MC
Proforma B-8
CRD 7 (a) - Progress regarding Kaccha/Brick Paved Roads to be made Pucca road (MC)
Sr. No. | Name of city | Baseline as on 31.03.2019 ( Katcha /Brick Paved roads identified ) (Km) | Targets (Katcha /Brick Paved roads to be made pucca road) (Km) | Timeline | Progress as on 30.04.2019 |  |  | Remarks of concerned Deptt./ officer (If any) | Remarks of DECC
[5 empty] | Tendering (Completed or Under Process) | Work allotment (Completed or Under Process) | Status of Work (Completed or in progress)
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10
1 | Mandi Gobindgarh | 25 | 25 | 31.03.2021
2 | Khanna | 0 | 0 | NA
3 | Jalandhar | 41 | 41 | 31.03.2021
4 | Ludhiana | 10.06 | 10.06 | 31.03.2020
5 | Patiala | 0.3 | 0.3 | 31.01.2020
6 | Amritsar | 0 | 0 | NA
7 | Nayan Nangal | 0 | 0 | NA
8 | DeraBassi | 4 | 4 | 31.12.2019
9 | Dera Baba Nanak | 0 | 0 | NA
| Total | 80.36 | 80.36
City-wise details of kaccha/brick paved to be made pacca roads - Supplementary Information
Name of the city :
Sr.No. | Name of the kaccha/brick paved to be made pacca roads |  |  | Road length (Kms)

## CRD 7 (b-i)MC
Proforma B-9
CRD 7 (b) - Progress regarding Existing roads requiring recarpeting (MC)
Sr. No. | Name of city | Baseline as on 31.03.2019 (Total length of exisiting roads) (Km) | Targets (Existing roads requiring recarpetting) (Km) | Timeline | Progress as on 30.04.2019 |  |  | Remarks of concerned Deptt./ officer (If any) | Remarks of DECC
[5 empty] | Tendering (Completed or Under Process) | Work allotment (Completed or Under Process) | Status of Work (Completed or in progress)
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10
1 | Mandi Gobindgarh | 0 | 0 | NA
2 | Khanna | 4.5 | 4.5 | 31.03.2020
3 | Jalandhar | 45 | 45 | 31.03.2021
4 | Ludhiana | 93.55 | 93.55 | 31.03.2020
5 | Patiala | 16.17 | 16.17 | 31.01.2020
6 | Amritsar | 28 | 28 | 31.03.2020
7 | Nayan Nangal | 10 | 10 | 30.09.2019
8 | DeraBassi | 0 | 0 | NA
9 | Dera Baba Nanak | 9.34 | 9.34 | 30.09.2019
| Total | 206.56 | 206.56
City-wise details of existing roads to be recarpeted - Supplementary Information
Name of the city :
Sr.No. | Name of the existing roads to be recarpeted |  |  | Road length (Kms)

## CRD 7 (c-i) MC
Proforma B-10
CRD 7 (c) -Pavement of road side using interlocking tiles(MC)
Sr. No. | Name of city | Baseline as on 31.03.2019 (Total length of berm identified along city roads) (Kms) | Targets (Length of berm identified for stabilization using interlocking tiles) (Kms) | Timeline | Progress as on 30.04.2019 |  |  | Remarks of concerned Deptt./ officer (If any) | Remarks of DECC
[5 empty] | Tendering (Completed or Under Process) | Work allotment (Completed or Under Process) | Status of Work (Completed or in progress)
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10
1 | Mandi Gobindgarh | 10 | 10 | 31.03.2020
2 | Khanna | 0 | 0 | NA
3 | Jalandhar | 1.6 | 1.6 | 31.03.2020
4 | Ludhiana | 0.8 | 0.8 | 30.09.2019
5 | Patiala | 3 | 3 | 31.01.2020
6 | Amritsar | 28 | 28 | 31.03.2020
7 | Nayan Nangal | 16 | 16 | 30.09.2019
8 | DeraBassi | 2 | 2 | 31.12.2019
9 | Dera Baba Nanak | 0 | 0 | NA
| Total | 61.4 | 61.4
City-wise details of pavement of road side using interlocking tiles - Supplementary Information
Name of the city :
Sr.No. | Name of the road to be paved using interlocking tiles |  |  | Road length (Kms)

## CVE 4 (ai) MC
Proforma B-11
CVE 4 (a) - Progress regarding creating parking infrastracture to prevent parking of vehicles in non-designated areas (MC)
Sr. No. | Name of city | Baseline as on 31.03.2019 |  |  | Targets |  |  | Timeline | Progress as on 30.04.2019 |  |  | Remarks of concerned Deptt./ officer (If any) | Remarks of DECC
|  | Designated parking lot site (Nos.) | Multi storey parking lots (Nos.) | Parking for trucks/ commercial (Nos.) | Designated parking lot site to be constructed (Nos.) | Multi storey parking lots to be constructed (Nos.) | Parking for trucks/ commercial to be constructed (Nos.) |  | Designated parking lot sites provided (Nos.) | Multi storey parking lots to be constructed (Nos.) | Parking for trucks/ commercial constructed (Nos.)
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 14 | 15
1 | Mandi Gobindgarh | 0 | 0 | 1 | 1 | 0 | 1 | 31.01.2020
2 | Khanna | 1 | 0 | 0 | 1 | 1 | 1 | 31.03.2020
3 | Jalandhar | 3 | 0 | 0 | 0 | 2 | 0 | 31.03.2021
4 | Ludhiana | 23 | 2 | 1 | 0 | 3 | 0 | 30.03.2022
5 | Patiala | 3 | 0 | 1 | 1 | 0 | 0 | 30.09.2019
6 | Amritsar | 2 | 4 | 1 | 3 | 2 | 0 | 31.03.2021
7 | Nayan Nangal | 0 | 0 |  |  |  |  | NA
8 | DeraBassi | 2 | 0 | 0 | 2 | 0 | 0 | 30.06.2021
9 | Dera Baba Nanak | 0 | 0 | 0 | 1 | 0 | 0 | 31.03.2020
| Total | 34 | 6 | 4 | 9 | 8 | 2

## CVE 4 (aii) MC
Proforma B-12
CVE 4 (a) - Progress regarding Prevent parking of vehicles in non-designated areas by enforcement actions (MC)
Sr. No. | Name of city | Baseline as on 31.03.2019 |  | Targets |  | Timeline | Progress as on 30.04.2019 |  |  | Remarks of concerned Deptt./ officer (If any) | Remarks of DECC
|  | Roadside parking earmarked by yellow line | "No Parking” sign Boards installed | Roadside parking to be earmarked by yellow line | No Parking” sign Boards to be installed |  | Roadside parking earmarked by yellow line |  | "No Parking” sign Boards installed (Nos.)
[7 empty] | No. of parking sites | Capacity of parking sites
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 12 | 13
1 | Mandi Gobindgarh | 4 | 0 | 4 | 50 | 31.12.2019
2 | Khanna | 0 | 10 | 0 | 10 | 31.12.2019
3 | Jalandhar | 6 | 200 | 4 | 150 | 31.12.2019
4 | Ludhiana | 18 | 16 | 0 | 40 | 30.09.2019
5 | Patiala | 3 | 1 | 2 | 0 | 30.09.2019
6 | Amritsar | 14 | 50 | 6 | 40 | 30.09.2019
7 | Nayan Nangal | 0 | 0 | 0 | 0 | NA
8 | DeraBassi | 0 | 0 | 0 | 0 | NA
9 | Dera Baba Nanak | 0 | 0 | 4 | 4 | 30.09.2019
| Total | 45 | 277 | 20 | 294

## CVE 6 (a-i) MC
Proforma B-13
CVE 6 (a) - Progress regarding Widening of roads and infrastructure for decongestion of roads (MC)
Sr. No. | Name of city | Baseline as on 31.03.2019 | Targets | Timeline | Progress as on 30.04.2019 |  |  | Remarks of concerned Deptt./ officer (If any) | Remarks of DECC
|  | Total road length identified for widening (Km) | Identified road length to be widened (Km) |  | Tendering (Completed or Under Process) | Work allotment(Completed or Under Process) | Status of Work ( Completed or Under Process)
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10
1 | Mandi Gobindgarh | 1.5 | 1.5 | 30.10.2019
2 | Khanna | 2.5 | 2.5 | 31.03.2020
3 | Jalandhar | 7.1 | 7.1 | 31.03.2020
4 | Ludhiana | 8 | 8 | 30.09.2019
5 | Patiala | 5.55 | 5.55 | 31.01.2020
6 | Amritsar | 7 | 7 | 30.09.2019
7 | Nayan Nangal | 0 | 0 | NA
8 | DeraBassi | 9 | 9 | 31.03.2020
9 | Dera Baba Nanak | 7.45 | 7.45 | 31.10.2019
| Total | 48.1 | 48.1

## CVE 6 (b-i) MC
Proforma B-14
CVE 6(b) - Progress regarding Road design improvement (MC)
Sr. No. | Name of city | Baseline as on 31.03.2019 | Targets |  |  | Timeline | Progress as on 30.04.2019 |  |  | Remarks of concerned Deptt./ officer (If any) | Remarks of DECC
|  | Road length constructed after proper redesigning (Km) | Road length to be redesigned and realligned (Km) | No. of chowks to be realigned and redesigned | No. of junctions to be realigned and redesigned |  | Road length redesigned and realligned (Km) | No. of chowks realigned and redesigned | No. of junctions ealigned and redesigned
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 12 | 13
1 | Mandi Gobindgarh | 0 | 0 | 0 | 0 | NA
2 | Khanna | 0 | 0 | 0 | 0 | NA
3 | Jalandhar | 0 | 0 | 0 | 0 | NA
4 | Ludhiana | 40 | 2.7 | 6 | 8 | 31.03.2021
5 | Patiala | 0 | 0 | 0 | 0 | NA
6 | Amritsar | 0 | 0 | 0 | 0 | NA
7 | Nayan Nangal | 0 | 0 | 0 | 0 | NA
8 | DeraBassi | 0 | 0 | 0 | 0 | NA
9 | Dera Baba Nanak | 0 | 0 | 0 | 0 | NA
| Total | 40 | 2.7 | 6 | 8

## CVE 8-i
Proforma C-5
CVE 8 - Progress regarding Construction of expressways/ bypasses to avoid congestion (PWD,PUDA & NHAI)
Sr. No. | Name of city | Baseline as on 31.03.2019 | Targets | Timeline | Progress as on 30.04.2019 |  |  | Remarks of concerned Deptt./ officer (If any) | Remarks of DECC
|  | Existing No. of bypass/ expressways | No. of bypass/ expressways to be constructed |  | Tendering (Completed or Under Process) | Work allotment (Completed or Under Process) | Status of Work (Completed or Under Process)
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 10 | 11
1 | Mandi Gobindgarh | 0 | 0
2 | Khanna | 0 | 0 | NA
3 | Jalandhar | 0 | 0 | NA
4 | Ludhiana | 0 | 1 | 30.06.2021
5 | Patiala | 0 | 0 | NA
6 | Amritsar | 0 | 0 | NA
7 | Nayan Nangal | 0 | 0 | NA
8 | DeraBassi | 0 | 0 | NA
9 | Dera Baba Nanak | 0 | 0 | NA
| Total | 0 | 1

## CVE 7 MC
Proforma B-15
CVE 7 - Progress regarding intelligent traffic systems (MC)
Sr. No. | Name of city | Baseline as on 31.03.2019 | Targets | Timeline | Progress as on 30.04.2019 |  |  | Remarks of concerned Deptt./ officer (If any) | Remarks of DECC
|  | No. of intellegent traffic lights already installed | No. of intellegent traffic lights to be introduced |  | Tendering (Completed or Under Process) | Work allotment (Completed or Under Process) | Status of Work (Completed or Under Process)
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 10 | 11
1 | Mandi Gobindgarh | 0 | 0 | NA
2 | Khanna | 0 | 2 | 30.10.2019
3 | Jalandhar | 0 | 11 | 31.03.2020
4 | Ludhiana | 0 | 0 | NA
5 | Patiala | 0 | 19 | 31.10.2019
6 | Amritsar | 0 | 21 | 31.05.2019
7 | Nayan Nangal | 0 | 0 | NA
8 | DeraBassi | 0 | 0 | NA
9 | Dera Baba Nanak | 0 | 0 | NA
| Total | 0 | 53

## CVE 11 (b) MC
Proforma B-16
CVE 11 (b) – Progress regarding introduction of CNG based city Bus Service (MC)
Sr. No. | Name of city | Baseline as on 31.03.2019 | Targets | Timeline | Progress as on 30.04.2019 | Remarks of concerned Deptt./ officer (If any) | Remarks of DECC
|  | No. of CNG based buses | Measures to be taken to introduce CNG buses |  | Measures taken to introduce CNG buses
1 | 2 | 3 | 4 | 6 | 7 | 11 | 12
1 | Mandi Gobindgarh | 0 | 0 | 31.03.2022
2 | Khanna | 0 | 0
3 | Jalandhar | 0 | 0
4 | Ludhiana | 0 | 0
5 | Patiala | 0 | 0
6 | Amritsar | 0 | 0
7 | Nayan Nangal | 0 | 0
8 | DeraBassi | 0 | 0
9 | Dera Baba Nanak | 0 | 0
Total

## CBGB 1
Proforma B-17
CBGB 1 – Progress regarding Control on open burning of bio-mass in City (MC)
Sr. No. | Name of city | Baseline as on 31.03.2019 | Targets | Timeline | Progress as on 30.04.2019 |  |  | Remarks of concerned Deptt./ officer (If any) | Remarks of DECC
|  | No. of pits constructed | No. of pucca pits to be constructed |  | Tendering (Completed or Under Process) | Work allotment(Completed or Under Process) | Status of Work ( Completed or Under Progress)
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 10 | 11
1 | Mandi Gobindgarh | 27 | 48 | 30.10.2019
2 | Khanna | 23 | 100 | 31.12.2019
3 | Jalandhar | 0 | 100 | 30.09.2019
4 | Ludhiana | 140 | 126 | 31.03.2020
5 | Patiala | 59 | 141 | 31.01.2020
6 | Amritsar | 6 | 19 | 30.09.2019
7 | Nayan Nangal | 20 | 0 | NA
8 | DeraBassi | 26 | 14 | 30.09.2019
9 | Dera Baba Nanak | 7 | 0 | NA
| Total | 308 | 548

## CBGB 2
Proforma B-18
CBGB 2 – Progress regarding Control on burning of municipal solid wastes (MC)
Sr. No. | Name of city | Baseline as on 31.03.2019 |  | Targets | Timeline | Progress as on 30.04.2019 |  | Remarks of concerned Deptt./ officer (If any) | Remarks of DECC
|  | No. of inspections made | No. of challans issued |  |  | No. of inspections made | No. of challans issued
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10
1 | Mandi Gobindgarh | 11 | 0 | 90 | 30.09.2019
2 | Khanna | 25 | 25 | 90
3 | Jalandhar | 4 | 4 | 270
4 | Ludhiana | 85 | 50 | 270
5 | Patiala | 36 | 36 | 180
6 | Amritsar | 31 | 28 | 270
7 | Nayan Nangal | 28 | 17 | 90
8 | Dera Bassi | 40 | 9 | 90
9 | Dera Baba Nanak | 2 | 0 | 90
| Total | 262 | 169 | 1440 | 30.09.2019

## CCDA 1(a) MC
Proforma B-19
CCDA 1 (a) – Progress regarding Enforcement of Construction & Demolition Waste Rules (MC)
Sr. No. | Name of city | Baseline as on 31.03.2019 |  | Targets (No. of inspections made) | Timeline | Progress as on 30.04.2019 |  | Remarks of concerned Deptt./ officer (If any) | Remarks of DECC
|  | No. of inspections made | No. of challans issued |  |  | No. of inspections made | No. of challans issued
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10
1 | Mandi Gobindgarh | 0 | 0 | 60 | 30.09.2019
2 | Khanna | 0 | 0 | 60
3 | Jalandhar | 0 | 0 | 150
4 | Ludhiana | 120 | 95 | 360
5 | Patiala | 100 | 21 | 300
6 | Amritsar | 3 | 3 | 150
7 | Nayan Nangal | 5 | 0 | 30
8 | DeraBassi | 40 | 9 | 120
9 | Dera Baba Nanak | 2 | 0 | 30
| Total | 270 | 128 | 1260 | 30.09.2019

## CCDA 2 MC
Proforma B-20
CCDA 2 – Progress regarding control measures for fugitive measures w.r.t Construction & Demolition Activities (MC)
Sr. No. | Name of city | Baseline as on 31.03.2019 |  | Targets (No. of inspections made) | Timeline | Progress as on 30.04.2019 |  | Remarks of concerned Deptt./ officer (If any) | Remarks of DECC
|  | No. of inspections made | No. of challans issued |  |  | No. of inspections made | No. of challans issued
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10
1 | Mandi Gobindgarh | 0 | 0 | 48 | 30.09.2019
2 | Khanna | 0 | 0 | 48
3 | Jalandhar | 0 | 0 | 48
4 | Ludhiana | 0 | 0 | 48
5 | Patiala | 80 | 21 | 48
6 | Amritsar | 0 | 0 | 48
7 | Nayan Nangal | 0 | 0 | 24
8 | DeraBassi | 0 | 0 | 24
9 | Dera Baba Nanak | 0 | 0 | 24
| Total | 80 | 21 | 360

## CCDA 3 MC
Proforma B-21
CCDA 3 – Progress regarding control measures for carrying the construction material enclosed/ covered vessels (MC)
Sr. No. | Name of city | Baseline as on 31.03.2019 |  | Targets (No. of inspections made) | Timeline | Progress as on 30.04.2019 |  | Remarks of concerned Deptt./ officer (If any) | Remarks of DECC
|  | No. of inspections made | No. of challans issued |  |  | No. of inspections made | No. of challans issued
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10
1 | Mandi Gobindgarh | 0 | 0 | 48 | 30.09.2019
2 | Khanna | 0 | 0 | 48
3 | Jalandhar | 0 | 0 | 48
4 | Ludhiana | 0 | 0 | 48
5 | Patiala | 0 | 0 | 48
6 | Amritsar | 0 | 0 | 48
7 | Nayan Nangal | 0 | 0 | 24
8 | DeraBassi | 0 | 0 | 24
9 | Dera Baba Nanak | 0 | 0 | 24
| Total | 0 | 0 | 360 | 30.09.2019

## CCDA 1(b) MC
Proforma B-22
CCDA 1 (b) – Progress regarding Infrastructure of Construction & Demolition waste (MC)
Sr. No. | Name of city | Baseline as on 31.03.2019 | Targets | Timeline | Progress as on 30.04.2019 |  | Remarks of concerned Deptt./ officer (If any) | Remarks of DECC
|  | No. of sites identified for C& D Waste disposal | No. of sites to be developed for C& D Waste disposal |  | Status of C& D waste site Development ( Completed or Under Process) | Quanitity of C & D waste processed/ recycled/disposed at C&D waste site.
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9
1 | Mandi Gobindgarh | 0 | 1 | 31.03.2022
2 | Khanna | 0 | 1 | 31.03.2022
3 | Jalandhar | 4 | 4 | 31.03.2022
4 | Ludhiana | 6 | 6 | 31.03.2021
5 | Patiala | 4 | 4 | 30.06.2019
6 | Amritsar | 5 | 0 | NA
7 | Nayan Nangal | 0 | 2 | 31.03.2022
8 | DeraBassi | 0 | 2 | 30.06.2019
9 | Dera Baba Nanak | 0 | 0 | NA
| Total | 19 | 20