## Summary Sheet PWD
Directoroate of Environment & Climate Change
Action Plan for Clean Air-Nine Non attainment cities
Summary : Activities pertaining to PWD
Sr No. | Activity | Measuring units/ Performance Indicator | Baseline as on 31.03.2019 | Targets | Timeline | Progress as on 30.04.2019
1 | CRD 1 (ii) : Maintain pothole free roads /Patch work of roads (PWD) | Identified road length made pothole free (Km) | 55.81 | 55.81 | 31.03.2020 | 9 Km completed, Work in progress for29.58 Km and A/A awaited for 17.23 Km
2 | CRD 7 (b-ii) - Progress regarding Existing roads requiring recarpeting (PWD) | Existing roads requiring recarpetting) (Km) | 96.99 | 96.99 | 31.03.2020 | Work in progress for 80.71 Km and A/A awaited for16.28 Km
3 | CRD 7 (c-ii) -Pavement of road side using interlocking tiles(PWD) | Length of berm stabilized by using interlocking tiles (Km) | 131.392 | 131.392 | 31.03.2021 | Work in progress for 52.782 Km
4 | CVE 6 (a) - Progress regarding Widening of roads and infrastructure for decongestion of roads (PWD) | Total road length identified for widening (Km) | 37.66 | 37.66 | 31.03.2021 | Work in progress for 16.36 Km and A/A awaited for 21.3 Km

## CRD 1(ii) PWD
Proforma C-1
CRD 1 (ii) : Maintain pothole free roads /Patch work of roads (PWD)
Sr. No. | Name of city | Baseline as on 31.03.2019 (Total road length with potholes Identified) (Km) | Targets (Identified road length to be made pothole free) (Km) | Timeline | Progress as on 30.04.2019 |  |  | Remarks of concerned Deptt./officer (If any) | Remarks of DECC
[5 empty] | Tendering (Completed or Under Process) | Work allotment (Completed or Under Process) | Status of Work (Completed or in progress)
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10
1 | Mandi Gobindgarh | 9 | 9 | 30.10.2019
2 | Khanna | 8.33 | 8.33 | 31.03.2020
3 | Jalandhar | 4.3 | 4.3 | 31.03.2021
4 | Ludhiana | 0 | 0 | NA
5 | Patiala | 20.58 | 20.58 | 30.10.2019
6 | Amritsar | 0 | 0 | NA
7 | Nayan Nangal | 9 | 9 | 31.07.2019
8 | DeraBassi | 0 | 0 | Nil
9 | Dera Baba Nanak | 4.6 | 4.6 | 30.09.2019
| Total | 55.81 | 55.81
City-wise details of roads made pothole free - Supplementary Information
Name of the city :
Sr.No. | Name of the road to be made pothole free |  |  | Road length (Kms)

## CRD 7(b-ii) PWD
Proforma C-2
CRD 7 (b) - Progress regarding Existing roads requiring recarpeting (PWD)
Sr. No. | Name of city | Baseline as on 31.03.2019 (Total length of exisiting roads) (Km) | Targets (Existing roads requiring recarpetting) (Km) | Timeline | Progress as on 30.04.2019 |  |  | Remarks of concerned Deptt./ officer (If any) | Remarks of DECC
[5 empty] | Tendering (Completed or Under Process) | Work allotment (Completed or Under Process) | Status of Work (Completed or in progress)
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10
1 | Mandi Gobindgarh | 0 | 0 | NA
2 | Khanna | 0 | 0 | NA
3 | Jalandhar | 5.06 | 5.06 | 31.03.2020
4 | Ludhiana | 6.62 | 6.62 | 30.09.2019
5 | Patiala | 44.01 | 44.01 | 31.01.2020
6 | Amritsar | 27.7 | 27.7 | 30.06.2019
7 | Nayan Nangal | 9 | 9 | 30.11.2019
8 | DeraBassi | 0 | 0 | NA
9 | Dera Baba Nanak | 4.6 | 4.6 | 3107.2019
| Total | 96.99 | 96.99
City-wise details of existing roads to be recarpeted - Supplementary Information
Name of the city :
Sr.No. | Name of the existing roads to be recarpeted |  |  | Road length (Kms)

## CRD 7 (c-ii) PWD
Proforma C-3
CRD 7 (c) -Pavement of road side using interlocking tiles (PWD)
Sr. No. | Name of city | Baseline as on 31.03.2019 (Total length of berm identified along city roads) (Kms) | Targets (Length of berm identified for stabilization using interlocking tiles) (Kms) | Timeline | Progress as on 30.04.2019 |  |  | Remarks of concerned Deptt./ officer (If any) | Remarks of DECC
[5 empty] | Tendering (Completed or Under Process) | Work allotment (Completed or Under Process) | Status of Work (Completed or in progress)
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10
1 | Mandi Gobindgarh | 53.84 | 53.84 | 31.03.2021
2 | Khanna | 8.33 | 8.33 | 31.07.2020
3 | Jalandhar | 0 | 0 | NA
4 | Ludhiana | 0 | 0 | NA
5 | Patiala | 52.782 | 52.782 | 31.12.2019
6 | Amritsar | 11.84 | 11.84 | 22.08.2019
7 | Nayan Nangal | 0 | 0 | NA
8 | DeraBassi | 0 | 0 | NA
9 | Dera Baba Nanak | 4.6 | 4.6 | 31.03.2020
| Total | 131.392 | 131.392
City-wise details of pavement of road side using interlocking tiles - Supplementary Information
Name of the city :
Sr.No. | Name of the road to be paved using interlocking tiles |  |  | Road length (Kms)
Note on D11: Author: To be carried out by PUDA

## CVE 6(a-ii)
Proforma C-4
CVE 6 (a) - Progress regarding Widening of roads and infrastructure for decongestion of roads (PWD)
Sr. No. | Name of city | Baseline as on 31.03.2019 | Targets | Timeline | Progress as on 30.04.2019 |  |  | Remarks of concerned Deptt./ officer (If any) | Remarks of DECC
|  | Total road length identified for widening (Km) | Identified road length to be widened (Km) |  | Tendering (Completed or Under Process) | Work allotment (Completed or Under Process) | Status of Work (Completed or Under Process)
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10
1 | Mandi Gobindgarh | 1.87 | 1.87 | 30.03.2021
2 | Khanna | 8.33 | 8.33 | 31.03.2020
3 | Jalandhar | 6.5 | 6.5 | 31.03.2020
4 | Ludhiana | 0 | 0 | NA
5 | Patiala | 14.96 | 14.96 | 31.12.2019
6 | Amritsar | 0 | 0 | NA
7 | Nayan Nangal | 1.4 | 1.4 | 07.06.2020
8 | DeraBassi | 0 | 0 | NA
9 | Dera Baba Nanak | 4.6 | 4.6 | 31.03.2020
| Total | 37.66 | 37.66