## Summary Sheet PPCB
Directoroate of Environment & Climate Change
Action Plan for Clean Air
Summary of activities related to PPCB
Sr No. | Activity | Measuring units/ Performance Indicator | Baseline as on 31.03.2019 | Targets | Timeline |  | Progress |  | Remarks of concerned Deptt. | Remarks of DECC
[6 empty] | 2019-04-01 | May,19 | Cummalative as on 31.05.2019
1 | 2 | 3 | 4 | 5 | 6 | 7 | 7 | 8 (4+7) | 9
1 | CIE-0: Air Quality Monitoring report by PPCB | PM 10 µg/m3 (Range for 09 cities) | 76-292 | 60 (Standard) | 30.09.2019 | 50-201 |  |  |  | aa
2 | CIE-1: Conversion to Side Hood Suction in Induction Furnaces | Nos | 25 | 163 | 30.09.2019 | 14
3 | CIE -2(i) :Industries to be converted from coal to CNG | Nos | 6 | 914 | 31.03.2021 | 6
4 | CIE 3: Conversion of Natural Draft Brick Kilns to Induced Draft Brick Kilns | Nos | 13 | 101 | 30.09.2019 | 11
4 (ii) | CIE 4: Action against non-complying Industrial units ( Out of 2279 industries located within 5 Km of MC limit) -Action at RO Level | % w, | 32 | 100% acti | 30.09.2019 |  |  |  | Achievement =_____%
4 (iii) | CIE 4: Action against non-complying Industrial units ( Out of 2279 industries located within 5 Km of MC limit) -Action at SEE Level | Nos | 0 |  | 30.09.2019 |  |  |  | SCN = ___Nos Closed =__ Nos
4 | CIE 4: Action against non-complying Industrial units ( Out of 2279 industries located within 5 Km of MC limit) -Action at CEE Level | Nos | 0 |  | 30.09.2019 |  |  |  | SCN = ___Nos Closed =__ Nos
5 | CIE 4 Action against non-complying Industrial units ( Out of 2279 industries located within 5 Km of MC limit) | Nos | 32 | 100% Action against all non-complying units | Regular inspections | 31 |  |  |  | 100% Achieved
6 | CBGB 3 – Control on burning of agriculture waste and crop residue | No of incident reported | 50479 during year 2018 | Zero stubble burning | Seasonal activity | 108
7 | COS 1 –Dissemination of Air Quality Index | i) No. CAAQMS installed ii) Nos of display Board | i) 06 ii) 01 | i) 10 ii) 09 | 31.03.2020 | i) 0 ii) 0
8 | COS 2 & 3 – Establish an Air Quality Management Division at SPCB HQ and helpline in each city as well as SPCB HQ | Set up /Not set up | No separate divisiion & helpline exists | Separate helpline on air quality management to be set up | 31.03.2020 | Not set up |  |  | -
9 | COS 4 – Monitoring of DG sets and actions against violations | i) DG sets Monitored (Nos) ii) Action against violators (Nos) | i) Monitored 8 Nos ii) SCN issued: 8 Nos & Action under process: 0 nos. | 312 | 30.09.2019 | i) Monitored 26 Nos ii) SCN issued: 3 Nos & Action under process: 5 nos.
10 | COS 5 – Source Apportionment Study (PPCB) | Nos of city covered | 2 | 9 | 31.03.2020
Note on I5: hp: Cumm. Progress includes base line data and progress of all previous months.
Note on E6: hp: Target inclues baseline figures

## Air Quality PPCB
Proforma A-0
Proforma for Air Quality Monitoring report by PPCB
Sr. No. | City | Monitoring Station (Locations at) | Baseline (Avg. Value of corresponding month of 2018) |  | Current Month (May 2019) ( Monthly Avg Air Quality ) |  | Cummulative Progress as on 31.05.2019 ( Monthly Avg Air Quality ) |  | %age Deviation from average value of corrospending month of 2018 |  | Remarks of PPCB/ concrned officer, if any | Remarks of DECC
|  |  | PM 10 | AQI | PM 10 | AQI | PM 10 | AQI | PM 10 | AQI
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13
1 | Mandi Gobindgarh | United Steels
Modi Oil Mill
Raj Steel
CAAQMS
Average
2 | Khanna | Markfed Vanaspati
As Sec School
CAAQMS
Average
3 | Jalandhar | PWSSB Guest House
PPCB Office Bldg
MC Office Bldg
ESI Hosp Bldg
CAAQMS
Average
4 | Ludhiana | Milk Plant
RO-PPCB
Nahar Spinning Mill
Vishwakarma Chowk
CAAQMS
Average
5 | Patiala | Ceylon Ind/Kains
Fire Brigade Office
(CAAQMS)
Average
6 | Amritsar | VM Chilling Centre
Nagina Soap Factory
CAAQMS
Average
7 | Nayan Nangal | NFL
PACL
Average
8 | DeraBassi | PCPL, Ramgarh
Winsome Yarn
Average
9 | Dera Baba Nanak | C-PYTE
| Standard µg/m3 (Annual) |  | 60
Note on J4: hp: (6-4/4)x100

## CIE 1 PPCB
Proforma A-1
CIE-1: Progress regarding conversion to Side Hood Suction in Induction Furnaces (PPCB)
Sr. No. | Name of city | Baseline as on 31.03.2019 (No. of Induction furnaces already converted to Side Hood Suction ) | Targets (Nos of Induction furnaces to be converted to Side Hood Suction | Timeline | Progress of May, 2019 No. of units that have |  |  | Cummulative Progress as on 31.05.2019 No. of units that have | Tentative emission redcution acheived. | Remarks of concerned Deptt./officer (If any) | Remarks of DECC
[5 empty] | taken design of side hood technology | started fabrication | converted to Side Hood Suction | Converted to Side Hood Suction
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 9 | 10 | 11
1 | Mandi Gobindgarh | 19 | 69 | 30.09.2019 |  |  |  |  | 50% (related to emissions of individual industry)
2 | Khanna | 3 | 13 | 30.09.2019 |  |  |  |  | 50% (related to emissions of individual industry)
3 | Jalandhar | 0 | 3 | 30.09.2019 |  |  |  |  | -
4 | Ludhiana | 3 | 74 | 30.09.2019
5 | Patiala | 0 | 0 | NA |  |  |  |  | -
6 | Amritsar | 0 | 0 | NA |  |  |  |  | -
7 | Nayan Nangal | 0 | 0 | NA
8 | DeraBassi | 0 | 4 | 30.09.2019 |  |  |  |  | Performance yet to be assessed.
9 | Dera Baba Nanak | 0 | 0 | NA |  |  |  |  | NA
| Total | 25 | 163
Note on C3: hp: Work completed upto 31.03.2019
Note on D3: hp: Targets includes baseline figures
Note on F3: hp: One month progess only
Note on I3: hp: Cumm. Progress inclues baseline and all previous months figures
Note on K3: hp: Reason for slow progress etc.
Note on F4: hp: only taking design
Note on G4: hp: This should be equal to or less than figure mentioned in coloumn 6
Note on H4: hp: This should be equal to or less than figure mentioned in coloumn 7
Note on I4: hp: Progress of all previous months ( April 19 +May 19+…...+Base line data)
Note on D5: hp: Taraget inclues Baseline figures

## CIE 2(i) PPCB
Proforma A-2
CIE -2(i) :Progress regarding industries to be converted from coal to CNG (PPCB)
Sr. No. | Name of city | Baseline as on 31.03.2019 (No of Industries already converted to CNG) | Targets (No of Industries to be converted to CNG) | Timeline | Progress of May, 2019 No. of unis that have |  | Cummulative progress as on 31.05.2019 No. of unis that have | Remarks of concerned Deptt./officer (If any) | Remarks of DECC | Remarks of DECC
[5 empty] | Signed agreement with CNG company | Converted to CNG | Converted to CNG
1 | 2 | 3 | 4 | 5 | 6 | 7 | 6 | 8 | 9 | 10
1 | Mandi Gobindgarh | 6 | 226 | 31.03.2021
2 | Khanna | 0 | 93 | 31.03.2021
3 | Jalandhar | 0 | 0 | NA
4 | Ludhiana | 0 | 500 | 31.03.2021
5 | Patiala | 0 | 0 | NA
6 | Amritsar | 0 | 95 | 31.03.2021
7 | Nayan Nangal | 0 | 0 | NA
8 | DeraBassi | 0 | 0 | NA
9 | Dera Baba Nanak | 0 | 0 | NA
| Total | 6 | 914
Note on H4: hp: Progress of all previous months ( April 19 +May 19+…...+Base line data)
Note on D5: hp: Target includes baseline figures

## CIE 3 PPCB
Proforma A-3
CIE 3:Progress regarding Conversion of Natural Draft Brick Kilns to Induced DraftBrick Kilns (PPCB)
Sr. No. | Name of city | Baseline as on 31.03.2019 (Nos of brick kilns already converted) | Targets (Nos of brick kilns to be converted) | Timeline | Progress of May, 2019 Nos of BKO that have |  |  | Cumm. progress as on 31.05.2019 Nos of BKO that have | Remarks of concerned Deptt./officer (If any) | Remarks of DECC
[5 empty] | taken design for induced draft technology | Started construction | Converted to Induced Draft | Converted to Induced Draft
1 | 2 | 3 | 4 | 5 | 6 |  | 7 | 6 | 8 | 9
1 | Mandi Gobindgarh | 0 | 0 | NA
2 | Khanna | 1 | 5 | 30.09.2019
3 | Jalandhar | 1 | 6 | 30.09.2019
4 | Ludhiana | 5 | 53 | 30.09.2019
5 | Patiala | 1 | 1 | NA
6 | Amritsar | 0 | 28 | 30.09.2019
7 | Nayan Nangal | 0 | 0 | NA
8 | DeraBassi | 5 | 8 | 30.09.2019
9 | Dera Baba Nanak | 0 | 0 | NA
| Total | 13 | 101
Note on I3: hp: Progress of all previous months ( April 19 +May 19+…...+Base line data)
Note on D5: hp: Target inclues baseline figures

## CIE 4 PPCB RO,SEE,CEE
Proforma A-4
CIE 4 Action against non-complying Industrial units (RO-PPCB)
Sr. No. | Name of city | Baseline as on 31.03.2019 (No. of Industries inspected) | Targets (Nos of air polluing industries within 5 Km of MC limit to be inspected) | Timeline for inspection of targetted units | Progress of May, 2019 |  |  |  |  | Cumm. Progress as on 31.05.2019
[5 empty] | Air polluting industries inspected |  |  | Action taken against non-complying industries |  | Air polluting industries inspected |  |  | Action taken against non-complying industries |  | Remarks of concerned Deptt./officer (If any) | Remarks of DECC
[5 empty] | No. of Industries inspected w.r.t Adequacy of APCD | No. of industries having adequate APCD | No. of Industries not complying (APCD not adequate) | SCN/ Bank guarantee taken etc. (Nos) | Unit closed (Nos) | No. of Industries inspected w.r.t Adequacy of APCD | No. of industries having adequate APCD | No. of Industries not complying (APCD not adequate) | SCN/ Bank guarantee taken etc. (Nos) | Unit closed (Nos)
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 6 | 7 | 8 | 9 | 10 | 11 | 12
1 | Mandi Gobindgarh | 26 | 378 | 30.09.2019
2 | Khanna | 36 | 212 | 30.09.2019
3 | Jalandhar | 41 | 233 | 30.09.2019
4 | Ludhiana | 140 | 1015 | 30.09.2019
5 | Patiala | 9 | 51 | 30.09.2019
6 | Amritsar | 57 | 247 | 30.09.2019
7 | Nayan Nangal | 1 | 6 | 30.09.2019
8 | DeraBassi | 10 | 132 | 30.09.2019
9 | Dera Baba Nanak | 0 | 5 | 30.09.2019
| Total | 320 | 2279
Proforma A-4
CIE 4 Action against non-complying Industrial units (SEE-PPCB)
Sr. No. | Name of city | Baseline as on 31.03.2019 (No. of Industries inspected) | Targets (Nos of air polluing industries within 5 Km of MC limit to be inspected) | Timeline for inspection of targetted units | Progress of May, 2019 |  |  |  |  | Cumm. Progress as on 31.05.2019
[5 empty] | Air polluting industries inspected |  |  | Action taken against non-complying industries |  | Air polluting industries inspected |  |  | Action taken against non-complying industries |  | Remarks of concerned Deptt./officer (If any) | Remarks of DECC
[5 empty] | No. of Industries inspected w.r.t Adequacy of APCD | No. of industries having adequate APCD | No. of Industries not complying (APCD not adequate) | SCN/ Bank guarantee taken etc. (Nos) | Unit closed (Nos) | No. of Industries inspected w.r.t Adequacy of APCD | No. of industries having adequate APCD | No. of Industries not complying (APCD not adequate) | SCN/ Bank guarantee taken etc. (Nos) | Unit closed (Nos)
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 6 | 7 | 8 | 9 | 10 | 11 | 12
1 | Mandi Gobindgarh | 0 | 38 | 30.09.2019
2 | Khanna | 0 | 21 | 30.09.2019
3 | Jalandhar | 0 | 23 | 30.09.2019
4 | Ludhiana | 0 | 101 | 30.09.2019
5 | Patiala | 0 | 5 | 30.09.2019
6 | Amritsar | 0 | 25 | 30.09.2019
7 | Nayan Nangal | 0 | 2 | 30.09.2019
8 | DeraBassi | 0 | 14 | 30.09.2019
9 | Dera Baba Nanak | 0 | 2 | 30.09.2019
| Total | 0 | 231
Proforma A-4
CIE 4 Action against non-complying Industrial units (CEE-PPCB)
Sr. No. | Name of city | Baseline as on 31.03.2019 (No. of Industries inspected) | Targets (Nos of air polluing industries within 5 Km of MC limit to be inspected) | Timeline for inspection of targetted units | Progress of May, 2019 |  |  |  |  | Cumm. Progress as on 31.05.2019
[5 empty] | Air polluting industries inspected |  |  | Action taken against non-complying industries |  | Air polluting industries inspected |  |  | Action taken against non-complying industries |  | Remarks of concerned Deptt./officer (If any) | Remarks of DECC
[5 empty] | No. of Industries inspected w.r.t Adequacy of APCD | No. of industries having adequate APCD | No. of Industries not complying (APCD not adequate) | SCN/ Bank guarantee taken etc. (Nos) | Unit closed (Nos) | No. of Industries inspected w.r.t Adequacy of APCD | No. of industries having adequate APCD | No. of Industries not complying (APCD not adequate) | SCN/ Bank guarantee taken etc. (Nos) | Unit closed (Nos)
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 6 | 7 | 8 | 9 | 10 | 11 | 12
1 | Mandi Gobindgarh | 0 | 19 | 30.09.2019
2 | Khanna | 0 | 11 | 30.09.2019
3 | Jalandhar | 0 | 12 | 30.09.2019
4 | Ludhiana | 0 | 51 | 30.09.2019
5 | Patiala | 0 | 3 | 30.09.2019
6 | Amritsar | 0 | 13 | 30.09.2019
7 | Nayan Nangal | 0 | 1 | 30.09.2019
8 | DeraBassi | 0 | 7 | 30.09.2019
9 | Dera Baba Nanak | 0 | 1 | 30.09.2019
| Total | 0 | 118
CIE 4 Action against non-complying Industrial units ( Overall-PPCB)
Sr. No. | Name of city | Baseline as on 31.03.2019 (No. of Industries inspected) | Targets (Nos of air polluing industries within 5 Km of MC limit to be inspected) | Timeline for inspection of targetted units | Progress of May, 2019 |  |  |  |  | Progress as on 31.05.2019
[5 empty] | Air polluting industries inspected |  |  | Action taken against non-complying industries |  | Air polluting industries inspected |  |  | Action taken against non-complying industries |  | Remarks of concerned Deptt./officer (If any) | Remarks of DECC
[5 empty] | No. of Industries inspected w.r.t Adequacy of APCD | No. of industries having adequate APCD | No. of Industries not complying (APCD not adequate) | SCN/ Bank guarantee taken etc. (Nos) | Unit closed (Nos) | No. of Industries inspected w.r.t Adequacy of APCD | No. of industries having adequate APCD | No. of Industries not complying (APCD not adequate) | SCN/ Bank guarantee taken etc. (Nos) | Unit closed (Nos)
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 6 | 7 | 8 | 9 | 10 | 11 | 12
1 | Mandi Gobindgarh | 26 | 435 | 30.09.2019
2 | Khanna | 36 | 244 | 30.09.2019
3 | Jalandhar | 41 | 268 | 30.09.2019
4 | Ludhiana | 140 | 1167 | 30.09.2019
5 | Patiala | 9 | 59 | 30.09.2019
6 | Amritsar | 57 | 285 | 30.09.2019
7 | Nayan Nangal | 1 | 9 | 30.09.2019
8 | DeraBassi | 10 | 153 | 30.09.2019
9 | Dera Baba Nanak | 0 | 8 | 30.09.2019
| Total | 320 | 2628
Note on K3: hp: Progress of all previous months ( April 19 +May 19+…...+Base line data)
Note on D6: hp: Target includes baseline figures
Note on D20: hp: 10 pecent check on RO inspection
Note on K20: hp: Progress of all previous months ( April 19 +May 19+…...+Base line data)
Note on D37: hp: 5% check on ZO inspection
Note on K37: hp: Progress of all previous months ( April 19 +May 19+…...+Base line data)
Note on K53: hp: Progress of all previous months ( April 19 +May 19+…...+Base line data)

## CBGB 3(PPCB)
Proforma A-5
CBGB 3 – Progress regarding Control on burning of agriculture waste and crop residue (PPCB)
Sr. No. | Name of city | Baseline as on 31.03.2019 |  |  | Targets | Timeline | Progress of May,2019 |  |  | Cumm. Progress as on 31.05.2019 |  |  | Remarks of concerned Deptt./ officer (% age devation w.r. t pervious year) | Remarks of DECC
|  | No of incident reported by PRSC & other means | No. of challans issued during last season | Environmental compensation imposed during last season (Rs.) |  |  | No of incident reported by PRSC & other means | No. of challans issued | Environmental compensation imposed | No of incident reported by PRSC & other means | No. of challans issued | Environmental compensation imposed
1 | 2 | 3 | 4 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16
1 | Mandi Gobindgarh |  | 182 | 587500 | Zero stubble buring / crop residue burning | Seasonal activity
2 | Khanna |  | 104 | 292500
3 | Jalandhar |  | 122 | 380000
4 | Ludhiana |  | 150 | 525000
5 | Patiala |  | 771 | 2632500
6 | Amritsar |  | 328 | 870000
7 | Nayan Nangal |  | 4 | 10000
8 | DeraBassi |  | 40 | 150000
9 | Dera Baba Nanak |  | 339 | 848750
| Total |  | 2044 | 6296250
Note on K3: hp: Base line data not to be considered in the progress
Note on N5: 12- Nos incident reported previous year by this time say 'X'/X *100

## COS 1 PPCB
Proforma A-6
COS 1 – Progress regarding Dissemination of Air Quality Index (PPCB)
Sr. No. | Name of city | Baseline as on 31.03.2019 |  |  | Targets |  | Timeline | Progress of May, 2019 |  | Cumm. Progress as on 31.05.2019 |  | Remarks of concerned Deptt./ officer (If any) | Remarks of DECC
|  | No.manual AAQMS already installed. | No. CAAQMS already installed. | No of Display Board installed | Additonal No.of CAAQMS to be installed | Additional No of Display Board to be installed |  | No. CAAQMS installed | No of Display Board installed | No. CAAQMS installed | No of Display Board installed
1 | 2 | 3 | 4 | 0 | 5 |  | 6 | 7 | 8 | 7 | 8 | 10 | 11
1 | Mandi Gobindgarh | 3 | 1 | 0 | 0 | 1 | NA
2 | Khanna | 2 | 1 | 0 | 0 | 1 | NA
3 | Jalandhar | 4 | 1 | 0 | 3 | 1 | 31.03.2020
4 | Ludhiana | 4 | 1 | 0 | 3 | 1 | 31.03.2020
5 | Patiala | 2 | 1 | 1 | 0 | 1 | NA
6 | Amritsar | 2 | 1 | 0 | 3 | 1 | 31.03.2020
7 | Nayan Nangal | 2 | 0 | 0 | 0 | 1 | NA
8 | DeraBassi | 2 | 0 | 0 | 1 | 1 | 31.03.2020
9 | Dera Baba Nanak | 1 | 0 | 0 | 0 | 1 | NA
| Total | 22 | 6 | 1 | 10 | 9 | [5 empty] | PPCB has taken up matter with CPCB for setting up of CAAQMS
Note on F4: admin: Baseline data not added in the target
Note on G4: hp: Other than Base line figures

## COS 2 -3 PPCB
Proforma A-7
COS 2 & 3 – Establish an Air Quality Management Division at SPCB HQ and helpline in each city as well as SPCB HQ (PPCB)
Sr. No. | Name of city | Baseline as on 31.03.2019 | Targets | Timeline | Progress as on May,2019 | Cumm. progress as on 31.05.2019 | Remarks of concerned Deptt./ officer (If any) | Remarks of DECC
[5 empty] | Set up/Not Set up | Set up/Not Set up
1 | 2 | 3 | 5 | 6 | 7 | 8 | 9 | 10
1 | PPCB HO Patiala | No separate divison/helpline on air quality management at HO | Separate divisiion and helpline on air quality management at HO to be set up | 31.03.2020
2 | RO PPCB Fatehgarh Sahib | No separate helpline on air quality management | Separate helpline on air quality management to be set up | 31.03.2020
3 | RO PPCB Jalandhar
4 | RO PPCB Ludhiana
5 | RO PPCB Patiala
6 | RO PPCB Amritsar
7 | RO PPCB Mohali
8 | RO PPCB Batala
| Total |  |  |  | PPCB has taken up matter with CPCB for clarification | PPCB has taken up matter with CPCB for clarification

## COS 4 PPCB
Proforma A-8
COS 4 – Monitoring of DG sets and actions against violations (PPCB)
Sr. No. | Name of city | Baseline as on 31.03.2019 |  |  | Targets (Min. nos. of DG sets to be inspected ) | Timeline | Progress of May, 2019 |  |  | Progress as on 31.05.2019 |  |  | Remarks of concerned Deptt./ officer (If any) | Remarks of DECC
|  | No. of DG sets monitored | No. of DG sets found violating norms | Action against violators (Nos.) |  |  | No. of DG sets inspected | No. of DG sets found violating norms | Action against violators | No. of DG sets inspected | No. of DG sets found violating norms | Action against violators (Nos.)
1 | 2 | 3 | 4 | 4 | 5 | 6 | 7 | 8 | 9 | 7 | 8 | 9 | 10 | 11
1 | Mandi Gobindgarh | 0 | 0 | 0 | 48 | 30.09.2019
2 | Khanna | 1 | 1 | 1 | 24
3 | Jalandhar | 1 | 1 | 1 | 48
4 | Ludhiana | 5 | 5 | 5 | 48
5 | Patiala | 0 | 0 | 0 | 24
6 | Amritsar | 1 | 1 | 1 | 48
7 | Nayan Nangal | 0 | 0 | 0 | 24
8 | DeraBassi | 0 | 0 | 0 | 24
9 | Dera Baba Nanak | 0 | 0 | 0 | 24
| Total | 8 | 8 | 8 | 312 | 30.09.2019
Note on F3: 2 DG sets inspection per week for larger district otherwise 1 inpsectin per week
Note on K3: hp: Progress of all previous months ( April 19 +May 19+…...+Base line data)
Note on E4: hp: i) SCN: ii) Sealed: iii) Action Under process:
Note on M4: hp: i) SCN: ii) Sealed: iii) Action Under process:

## COS 5 PPCB
Proforma A-9
COS 5 – Source Apportionment Study (PPCB)
Sr. No. | Name of city | Baseline as on 31.03.2019 | Targets | Timeline | Progress of May,2019 | Cumm. progress as on 31.05.2019 |  | Remarks of concerned Deptt./ officer (If any) | Remarks of DECC
|  | Source Apportionment Studies conducted (Yes/No) | Source Apportionment Studies to be conducted (Yes/No) |  | Status of study conducted (Yes/No) | Name of the agency selected for conducting study | Status of study conducted (Yes/No)
1 | 2 | 3 | 5 | 6 | 7 | 7 | 8 | 10 | 11
1 | Mandi Gobindgarh | No | Yes | 31.03.2020
2 | Khanna | No | Yes
3 | Jalandhar | No | Yes
4 | Ludhiana | Yes | No
5 | Patiala | No | Yes
6 | Amritsar | Yes | No
7 | Nayan Nangal | No | Yes
8 | DeraBassi | No | Yes
9 | Dera Baba Nanak | No | Yes
| Nos of city covered | 1 | 8
Note on I3: hp: i) MOU status ii) Primary study status iii) Secondary study status iv) Percentage of study completed etc.