## Summary Sheet PUDA
Directoroate of Environment & Climate Change
Action Plan for Clean Air-Nine Non attainment cities
Summary : Activities pertaining to PUDA
Sr No. | Activity | Measuring units/ Performance Indicator | Baseline as on 31.03.2019 | Targets | Timeline | Progress as on 30.04.2019
1 | CRD 1 (iii) : Maintain pothole free roads /Patch work of roads (PUDA) | Identified road length made pothole free (Km) | 21.3 | 21.23 | 30.06.2019 | Tendering completed
2 | CVE 6 (a) - Progress regarding Widening of roads and infrastructure for decongestion of roads (PUDA) | Total road length identified for widening (Km) | 23.54 | 23.54 | 31.03.2021 | Tendeing under progress
3 | CRD 7 (a-ii) - Progress regarding Kaccha/Brick Paved Roads to be made Pucca road (PUDA) | Katcha /Brick Paved roads made pucca road (Km) | 10.87 | 10.87 | 31.03.2020 | Tendering completed for 8.32 Km
4 | CRD 7 (b-iii) - Progress regarding Existing roads requiring recarpeting (PUDA) | Existing roads requiring recarpetting) (Km) | 12 | 12 | 31.03.2020 | Tendering completed
5 | CRD 7 (c) -Pavement of road side using interlocking tiles ( PUDA) | Berm stabilized using interlocking tiles) (Kms) | 11.84 | 11.84 | 22.08.2019 | Tendering completed
Note on E10: Author: To be carried out by PUDA

## CRD 1 (iii) PUDA
Proforma- D-1
CRD 1 (iii) : Maintain pothole free roads /Patch work of roads (PUDA)
Sr. No. | Name of city | Baseline as on 31.03.2019 (Total road length with potholes Identified) (Km) | Targets (Identified road length to be made pothole free) (Km) | Timeline | Progress as on 30.04.2019 |  |  | Remarks of concerned Deptt./officer (If any) | Remarks of DECC
[5 empty] | Tendering (Completed or Under Process) | Work allotment (Completed or Under Process) | Status of Work (Completed or in progress)
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10
1 | Mandi Gobindgarh | 0 | 0 | NA
2 | Khanna | 0 | 0 | NA
3 | Jalandhar | 0 | 0 | NA
4 | Ludhiana | 0 | 0 | NA
5 | Patiala | 21.3 | 21.23 | 30.06.2019
6 | Amritsar | 0 | 0 | NA
7 | Nayan Nangal | 0 | 0 | NA
8 | DeraBassi | 0 | 0 | NA
9 | Dera Baba Nanak | 0 | 0 | NA
| Total | 21.3 | 21.23
City-wise details of roads made pothole free - Supplementary Information
Name of the city :
Sr.No. | Name of the road to be made pothole free |  |  | Road length (Kms)

## CVE 6(a-iii) PUDA
Proforma- D-2
CVE 6 (a) - Progress regarding Widening of roads and infrastructure for decongestion of roads (PUDA)
Sr. No. | Name of city | Baseline as on 31.03.2019 | Targets | Timeline | Progress as on 30.04.2019 |  |  | Remarks of concerned Deptt./ officer (If any) | Remarks of DECC
|  | Total road length identified for widening (Km) | Identified road length to be widened (Km) |  | Tendering (Completed or Under Process) | Work allotment (Completed or Under Process) | Status of Work (Completed or Under Process)
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10
1 | Mandi Gobindgarh | 0 | 0 | NA
2 | Khanna | 0 | 0 | NA
3 | Jalandhar | 2.4 | 2.4 | 30.06.2019
4 | Ludhiana | 21.14 | 21.14 | 31.03.2020
5 | Patiala | 0 | 0 | NA
6 | Amritsar | 0 | 0 | NA
7 | Nayan Nangal | 0 | 0 | NA
8 | DeraBassi | 0 | 0 | NA
9 | Dera Baba Nanak | 0 | 0 | NA
| Total | 23.54 | 23.54

## CRD 7 (a-ii) PUDA
Proforma- D-3
CRD 7 (a) - Progress regarding Kaccha/Brick Paved Roads to be made Pucca road (PUDA)
Sr. No. | Name of city | Baseline as on 31.03.2019 (Total Katcha /Brick Paved roads) (Km) | Targets (Katcha /Brick Paved roads to be made pucca road) (Km) | Timeline | Progress as on 30.04.2019 |  |  | Remarks of concerned Deptt./ officer (If any) | Remarks of DECC
[5 empty] | Tendering (Completed or Under Process) | Work allotment (Completed or Under Process) | Status of Work (Completed or in progress)
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10
1 | Mandi Gobindgarh | 0 | 0 | NA
2 | Khanna | 0 | 0 | NA
3 | Jalandhar | 2.4 | 2.4 | 31.07.2019
4 | Ludhiana | 0 | 0 | NA
5 | Patiala | 0 | 0 | NA
6 | Amritsar | 8.47 | 8.47 | 31.03.2020
7 | Nayan Nangal | 0 | 0 | NA
8 | DeraBassi | 0 | 0 | NA
9 | Dera Baba Nanak | 0 | 0 | NA
| Total | 10.87 | 10.87
City-wise details of kaccha/brick paved to be made pacca roads - Supplementary Information
Name of the city :
Sr.No. | Name of the kaccha/brick paved to be made pacca roads |  |  | Road length (Kms)

## CRD 7(b-iii) PUDA
Proforma- D-4
CRD 7 (b) - Progress regarding Existing roads requiring recarpeting (PUDA)
Sr. No. | Name of city | Baseline as on 31.03.2019 (Total length of exisiting roads) (Km) | Targets (Existing roads requiring recarpetting) (Km) | Timeline | Progress as on 30.04.2019 |  |  | Remarks of concerned Deptt./ officer (If any) | Remarks of DECC
[5 empty] | Tendering (Completed or Under Process) | Work allotment (Completed or Under Process) | Status of Work (Completed or in progress)
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10
1 | Mandi Gobindgarh | 0 | 0 | NA
2 | Khanna | 0 | 0 | NA
3 | Jalandhar | 0 | 0 | NA
4 | Ludhiana | 5.24 | 5.24 | 30.05.2019
5 | Patiala | 6.7 | 6.7 | 30.06.2019
6 | Amritsar | 0.06 | 0.06 | 31.03.2020
7 | Nayan Nangal | 0 | 0 | NA
8 | DeraBassi | 0 | 0 | NA
9 | Dera Baba Nanak | 0 | 0 | NA
| Total | 12 | 12
City-wise details of existing roads to be recarpeted - Supplementary Information
Name of the city :
Sr.No. | Name of the existing roads to be recarpeted |  |  | Road length (Kms)

## CRD 7 (c-ii) PUDA
Proforma- D-5
CRD 7 (c) -Pavement of road side using interlocking tiles (PWD & PUDA)
Sr. No. | Name of city | Baseline as on 31.03.2019 (Total length of berm identified along city roads) (Kms) | Targets (Length of berm identified for stabilization using interlocking tiles) (Kms) | Timeline | Progress as on 30.04.2019 |  |  | Remarks of concerned Deptt./ officer (If any) | Remarks of DECC
[5 empty] | Tendering (Completed or Under Process) | Work allotment (Completed or Under Process) | Status of Work (Completed or in progress)
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10
1 | Mandi Gobindgarh | 53.84 | 53.84 | 31.03.2021
2 | Khanna | 8.33 | 8.33 | 31.07.2020
3 | Jalandhar | 0 | 0 | NA
4 | Ludhiana | 0 | 0 | NA
5 | Patiala | 52.782 | 52.782 | 31.12.2019
6 | Amritsar | 11.84 | 11.84 | 22.08.2019
7 | Nayan Nangal | 0 | 0 | NA
8 | DeraBassi | 0 | 0 | NA
9 | Dera Baba Nanak | 4.6 | 4.6 | 31.03.2020
| Total | 131.392 | 131.392
City-wise details of pavement of road side using interlocking tiles - Supplementary Information
Name of the city :
Sr.No. | Name of the road to be paved using interlocking tiles |  |  | Road length (Kms)
Note on D11: Author: To be carried out by PUDA

## CVE 8-i PUDA
Proforma- D-6
CVE 8 - Progress regarding Construction of expressways/ bypasses to avoid congestion (MC,PUDA & NHAI)
Sr. No. | Name of city | Baseline as on 31.03.2019 | Targets | Timeline | Progress as on 30.04.2019 |  |  | Remarks of concerned Deptt./ officer (If any) | Remarks of DECC
|  | Existing No. of bypass/ expressways | No. of bypass/ expressways to be constructed |  | Tendering (Completed or Under Process) | Work allotment (Completed or Under Process) | Status of Work (Completed or Under Process)
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 10 | 11
1 | Mandi Gobindgarh | 1 | 0 | NA
2 | Khanna | 1 | 0 | NA
3 | Jalandhar | 1 | 1 | 30.09.2019
4 | Ludhiana | 2 | 3 | 30.06.2021
5 | Patiala | 2 | 0 | NA
6 | Amritsar | 5 | 2 | 30.06.2019
7 | Nayan Nangal | 0 | 0 | NA
8 | DeraBassi | 1 | 0 | NA
9 | Dera Baba Nanak | 0 | 0 | NA
| Total | 13 | 6
Note on D9: Author: NHAI : 1 Nos PWD : 1 Nos PUDA: 1 Nos
Note on D11: Author: NHAI : 2 Nos