## Summary Sheet TP
Directoroate of Environment & Climate Change
Action Plan for Clean Air-Nine Non attainment cities
Summary : Activities pertaining to Traffic Police
Sr No. | Activity | Measuring units/ Performance Indicator | Baseline as on 31.03.2019 | Targets | Timeline | Progress as on 31.05.2019
1 | CVE 1 - Progress regarding Public awareness campaign for control of vehicular emissions (Traffic Police) | Nos of Public awareness campaigns | 1336 | Public awareness campaigns to be contiued | Regular Activity
2 | CVE 3 - Progress regarding Extensive drive against polluting vehicles (Traffic Police) | No. of challans issued | 5884 | Regular inspection and challaning of polluting vehicles | Regular activity
3 | CVE 4 (b) - Progress regarding Prevent parking of vehicles in non-designated areas by enforcement actions (Traffic Police) | No. of challans | 37116 | Regular inspection and challaning of vehicles parked in the non-designated areas | Regular Activity

## CVE 1 ii TP
Proforma F-1
CVE 1 - Progress regarding Public awareness campaign for control of vehicular emissions (Traffic Police)
Sr. No. | Name of city | Baseline as on 31.03.2019 | Targets (No. of awareness activites to be organized during 2019) | Timeline | Progress of May,2019 |  | Cumm. progress as on 31.05.2019 |  | Remarks of concerned Deptt./ officer (If any) | Remarks of DECC
|  | No. of awareness activities organized |  |  | No. of awareness activities organised | No of Participants | No. of awareness activities organised | No of Participants
1 | 2 | 3 | 4 | 5 | 6 | 7 | 6 | 7 | 8
1 | Mandi Gobindgarh | 17 | Public awareness campaigns to be continued | Regular Activity
2 | Khanna | 6
3 | Jalandhar | 531
4 | Ludhiana | 212
5 | Patiala | 29
6 | Amritsar | 493
7 | Nayan Nangal | 24
8 | DeraBassi | 24
9 | Dera Baba Nanak | 0
Total
Note on H3: hp: Cumm. Progress inclues progrss of April,19 + May,19+…). No base line data to be added

## CVE 3 TP
Proforma F-2
CVE 3 - Progress regarding Extensive drive against polluting vehicles (Traffic Police)
Sr. No. | Name of city | Baseline as on 31.03.2019 | Targets | Timeline | Progress of May, 2019 | Cumm. progress as on 31.05.2019 | Remarks of concerned Deptt./ officer (If any) | Remarks of DECC
|  | No. of challans issued |  |  | No. of challans issued | No. of challans issued
1 | 2 | 3 | 4 | 5 | 6 | 6 | 7
1 | Mandi Gobindgarh | 161 | Regular inspection and challaning of polluting vehicles | Regular activity
2 | Khanna | 159
3 | Jalandhar | 1825
4 | Ludhiana | 994
5 | Patiala | 71
6 | Amritsar | 2218
7 | Nayan Nangal | 4
8 | DeraBassi | 2
9 | Dera Baba Nanak | 450
Total
Note on G3: hp: Cumm. Progress inclues progrss of April,19 + May,19 +…..)

## CVE 4 (b) TP
Proforma F-3
CVE 4 (a) - Progress regarding Prevent parking of vehicles in non-designated areas by enforcement actions (Traffic Police)
Sr. No. | Name of city | Baseline as on 31.03.2019 | Targets | Timeline | Progress of May,2019 | Cumm. progress as on 31.05.2019 | Remarks of concerned Deptt./ officer (If any) | Remarks of DECC
|  | No. of challans issued |  |  | No. of challans issued | No. of challans issued
1 | 2 | 3 | 4 | 5 | 6 | 6 | 7 | 8
1 | Mandi Gobindgarh | 176 | Regular inspection and challaning of vehicles parked in the non-designated areas | Regular
2 | Khanna | 204
3 | Jalandhar | 24273
4 | Ludhiana | 7734
5 | Patiala | 379
6 | Amritsar | 4201
7 | Nayan Nangal | 4
8 | DeraBassi | 145
9 | Dera Baba Nanak | 0
| Total | 37116
Note on G3: hp: Cumm. Progress inclues progrss of April,19 + May,19 +…..)